## Sheet1
Task | Start | Duration | Assigned To | End | Erledigt
Installation and Configuration of Playwright | 2024-10-30 11:35 | 1 | Hiba, Irina und Heiko | 2024-10-30 12:30 | x
Project and Test Structure Setup | 2024-10-30 11:35 | 1 | Hiba, Irina und Heiko | 2024-10-30 12:30 | x
Test Strategy and Requirement Analysis | 2024-10-30 18:00 | 1 | All Team Members (Meeting) | 2024-10-30 20:00
Creating Test Cases for Main Pages | 2024-11-04 | 2 | Team Member 1 and 2 | 2024-11-05
Creating Test Cases for Subpages | 2024-11-06 | 2 | Team Member 3 and 4 | 2024-11-07
Developing UI Test Scripts | 2024-11-08 | 2 | Team Member 1 and 3 | 2024-11-09
Automated Visual Regression Tests | 2024-11-10 | 1 | Team Member 2 and 4 | 2024-11-10
Conducting Performance Tests | 2024-11-11 | 1 | Team Member 1 and 2 | 2024-11-11
Cross-Browser Tests with Playwright | 2024-11-12 | 1 | Team Member 3 and 4 | 2024-11-12
Collecting and Documenting Results | 2024-11-13 | 1 | All Team Members | 2024-11-13
Final Meeting and Bug Fixes | 2024-11-14 | 1 | All Team Members | 2024-11-14
Introduction and Overview of Web App | 2024-11-15 | 1 | Documentation Team | 2024-11-15
Define Test Strategy and Methodology | 2024-11-16 | 1 | Documentation Team | 2024-11-16
Describe Test Environment | 2024-11-17 | 1 | Documentation Team | 2024-11-17
Tasks and Responsibilities Documentation | 2024-11-18 | 1 | Documentation Team | 2024-11-18
Create Test Cases and Test Data Documentation | 2024-11-19 | 1 | Documentation Team | 2024-11-19
Compile Error Reports | 2024-11-20 | 1 | Documentation Team | 2024-11-20
Test Summary and Recommendations | 2024-11-21 | 1 | Documentation Team | 2024-11-21
Finalize and Review Documentation | 2024-11-22 | 1 | All Team Members | 2024-11-22